## Role Aliases
Alias | Canonical Role
Business Analyst | Functional Consultant
Platform Lead | Technical Architect
Integration Developer | Integration Engineer
Integration Consultant | Integration Engineer
Extensibility Developer | Extensibility Engineer
DW Scribe | DegreeWorks Scribe
Degree Works Scribe | DegreeWorks Scribe

## Inputs
Parameter | Value
Baseline Total Hours | 6700

## Stage Weights
Phase | Stage | Stage Weight %
Discovery | Start | 0.025
Discovery | Prepare | 0.025
Build | Sprint 0 | 0.06
Build | Plan | 0.1
Build | Configure | 0.34
Build | Test | 0.2
Build | Deploy | 0.1
Optimize | Go-Live | 0.06
Optimize | Post Go-Live (Care) | 0.09

## Stages
Phase | Stage | Default Presales %
Discovery | Start | 0.6
Discovery | Prepare | 0.3
Build | Sprint 0 | 0
Build | Plan | 0
Build | Configure | 0
Build | Test | 0
Build | Deploy | 0
Optimize | Go-Live | 0
Optimize | Post Go-Live (Care) | 0

## Activities
Stage | Activity | Activity Weight | Is Presales
Start | Discovery Planning | 0.6 | TRUE
Start | Initial Assessment | 0.4 | FALSE
Prepare | Requirements Gathering | 0.3 | TRUE
Prepare | Solution Design | 0.7 | FALSE

## Role Mix
Stage | Role | Role Mix %
Start | Project Manager | 0.2
Start | Solution Architect | 0.3
Start | Technical Architect | 0.05
Start | Functional Consultant | 0.35
Start | QA Engineer | 0.1
Prepare | Project Manager | 0.15
Prepare | Solution Architect | 0.35
Prepare | Functional Consultant | 0.45
Prepare | QA Engineer | 0.05
Sprint 0 | Project Manager | 0.15
Sprint 0 | Solution Architect | 0.25
Sprint 0 | Functional Consultant | 0.5
Sprint 0 | QA Engineer | 0.1
Plan | Project Manager | 0.25
Plan | Solution Architect | 0.2
Plan | Technical Architect | 0.05
Plan | Functional Consultant | 0.4
Plan | QA Engineer | 0.1
Configure | Project Manager | 0.1
Configure | Solution Architect | 0.15
Configure | Technical Architect | 0.28
Configure | Functional Consultant | 0.2
Configure | QA Engineer | 0.1
Configure | Integration Lead | 0.07
Configure | Integration Engineer | 0.06
Configure | Extensibility Engineer | 0.04
Test | Project Manager | 0.15
Test | Solution Architect | 0.1
Test | Technical Architect | 0.04
Test | Functional Consultant | 0.15
Test | QA Engineer | 0.4
Test | Integration Engineer | 0.06
Test | Extensibility Engineer | 0.1
Deploy | Project Manager | 0.2
Deploy | Solution Architect | 0.15
Deploy | Technical Architect | 0.06
Deploy | Functional Consultant | 0.1
Deploy | QA Engineer | 0.2
Deploy | Integration Engineer | 0.15
Deploy | Extensibility Engineer | 0.14
Go-Live | Project Manager | 0.25
Go-Live | Solution Architect | 0.2
Go-Live | Functional Consultant | 0.45
Go-Live | QA Engineer | 0.1
Post Go-Live (Care) | Project Manager | 0.3
Post Go-Live (Care) | Solution Architect | 0.25
Post Go-Live (Care) | Functional Consultant | 0.35
Post Go-Live (Care) | QA Engineer | 0.1

## Rates
Role | Onshore Rate | Offshore Rate | Partner Rate
Project Manager | 150 | 75 | 120
Solution Architect | 175 | 90 | 140
Functional Consultant | 160 | 85 | 130
QA Engineer | 140 | 70 | 110
Integration Engineer | 130 | 65 | 100
Technical Architect | 170 | 85 | 135
Integration Lead | 180 | 95 | 145
Reporting Consultant | 165 | 80 | 125
Extensibility Engineer | 155 | 80 | 125
DegreeWorks Scribe | 145 | 72 | 116

## Delivery Mix
Role | Onshore % | Offshore % | Partner %
| 0.7 | 0.2 | 0.1
Project Manager | 0.8 | 0.15 | 0.05
Solution Architect | 0.75 | 0.2 | 0.05

## Legacy→N2S Mapping
Legacy Phase | N2S Stage | Allocation %
Discover | Start | 0.5
Discover | Prepare | 0.5
Design | Sprint 0 | 0.4
Design | Configure | 0.6
Build | Configure | 1
Deploy | Deploy | 1
Support | Post Go-Live (Care) | 1

## Add-On Catalog
Package | Tier | Role | Unit Hours | Role % | Scale By Size
Integrations | Simple | Integration Engineer | 80 | 0.6 | 0
Integrations | Simple | Technical Architect | 80 | 0.25 | 0
Integrations | Simple | QA Engineer | 80 | 0.1 | 0
Integrations | Simple | Project Manager | 80 | 0.05 | 0
Integrations | Standard | Integration Engineer | 160 | 0.5 | 0
Integrations | Standard | Technical Architect | 160 | 0.3 | 0
Integrations | Standard | QA Engineer | 160 | 0.15 | 0
Integrations | Standard | Project Manager | 160 | 0.05 | 0
Integrations | Complex | Integration Engineer | 320 | 0.45 | 0
Integrations | Complex | Technical Architect | 320 | 0.3 | 0
Integrations | Complex | Integration Lead | 320 | 0.15 | 0
Integrations | Complex | QA Engineer | 320 | 0.1 | 0
Reports | Simple | Reporting Consultant | 24 | 0.7 | 0
Reports | Simple | Solution Architect | 24 | 0.2 | 0
Reports | Simple | QA Engineer | 24 | 0.05 | 0
Reports | Simple | Project Manager | 24 | 0.05 | 0
Reports | Standard | Reporting Consultant | 72 | 0.6 | 0
Reports | Standard | Solution Architect | 72 | 0.25 | 0
Reports | Standard | QA Engineer | 72 | 0.1 | 0
Reports | Standard | Project Manager | 72 | 0.05 | 0
Reports | Complex | Reporting Consultant | 160 | 0.55 | 0
Reports | Complex | Solution Architect | 160 | 0.25 | 0
Reports | Complex | QA Engineer | 160 | 0.15 | 0
Reports | Complex | Project Manager | 160 | 0.05 | 0
Degree Works | Setup | DegreeWorks Scribe | 300 | 0.7 | 1
Degree Works | Setup | Functional Consultant | 300 | 0.2 | 1
Degree Works | Setup | Technical Architect | 300 | 0.1 | 1
Degree Works | PVE Simple | DegreeWorks Scribe | 24 | 0.7 | 0
Degree Works | PVE Simple | Functional Consultant | 24 | 0.2 | 0
Degree Works | PVE Simple | Technical Architect | 24 | 0.1 | 0
Degree Works | PVE Standard | DegreeWorks Scribe | 48 | 0.6 | 0
Degree Works | PVE Standard | Functional Consultant | 48 | 0.25 | 0
Degree Works | PVE Standard | Technical Architect | 48 | 0.15 | 0
Degree Works | PVE Complex | DegreeWorks Scribe | 96 | 0.5 | 0
Degree Works | PVE Complex | Functional Consultant | 96 | 0.3 | 0
Degree Works | PVE Complex | Technical Architect | 96 | 0.2 | 0

## Product Role Map
Role | Banner Enabled | Colleague Enabled | Multiplier
Project Manager | 1 | 1 | 1
Solution Architect | 1 | 1 | 1
Functional Consultant | 1 | 1 | 1
QA Engineer | 1 | 1 | 1
Integration Engineer | 1 | 1 | 1
Technical Architect | 1 | 0 | 1
Integration Lead | 1 | 0 | 1
Reporting Consultant | 1 | 1 | 1
Extensibility Engineer | 1 | 1 | 1
DegreeWorks Scribe | 1 | 0 | 1

## Rates (Locales)
Role | Locale | Onshore Rate | Offshore Rate | Partner Rate
Project Manager | US | 150 | 75 | 120
Solution Architect | US | 175 | 90 | 140
Functional Consultant | US | 160 | 85 | 130
QA Engineer | US | 140 | 70 | 110
Integration Engineer | US | 130 | 65 | 100
Technical Architect | US | 170 | 85 | 135
Integration Lead | US | 180 | 95 | 145
Reporting Consultant | US | 165 | 80 | 125
Extensibility Engineer | US | 155 | 80 | 125
DegreeWorks Scribe | US | 145 | 72 | 116
Project Manager | Canada | 142 | 71 | 114
Solution Architect | Canada | 166 | 85 | 133
Functional Consultant | Canada | 152 | 80 | 123
QA Engineer | Canada | 133 | 66 | 104
Integration Engineer | Canada | 123 | 61 | 95
Technical Architect | Canada | 161 | 80 | 128
Integration Lead | Canada | 171 | 90 | 137
Reporting Consultant | Canada | 156 | 76 | 118
Extensibility Engineer | Canada | 147 | 76 | 118
DegreeWorks Scribe | Canada | 137 | 68 | 110
Project Manager | UK | 165 | 82 | 132
Solution Architect | UK | 192 | 99 | 154
Functional Consultant | UK | 176 | 93 | 143
QA Engineer | UK | 154 | 77 | 121
Integration Engineer | UK | 143 | 71 | 110
Technical Architect | UK | 187 | 93 | 148
Integration Lead | UK | 198 | 104 | 159
Reporting Consultant | UK | 181 | 88 | 137
Extensibility Engineer | UK | 170 | 88 | 137
DegreeWorks Scribe | UK | 159 | 79 | 127
Project Manager | EU | 157 | 78 | 126
Solution Architect | EU | 183 | 94 | 147
Functional Consultant | EU | 168 | 89 | 136
QA Engineer | EU | 147 | 73 | 115
Integration Engineer | EU | 136 | 68 | 105
Technical Architect | EU | 178 | 89 | 141
Integration Lead | EU | 189 | 99 | 152
Reporting Consultant | EU | 173 | 84 | 131
Extensibility Engineer | EU | 162 | 84 | 131
DegreeWorks Scribe | EU | 152 | 75 | 121
Project Manager | ANZ | 172 | 86 | 138
Solution Architect | ANZ | 201 | 103 | 161
Functional Consultant | ANZ | 184 | 97 | 149
QA Engineer | ANZ | 161 | 80 | 126
Integration Engineer | ANZ | 149 | 74 | 114
Technical Architect | ANZ | 195 | 97 | 155
Integration Lead | ANZ | 206 | 109 | 166
Reporting Consultant | ANZ | 189 | 92 | 143
Extensibility Engineer | ANZ | 178 | 92 | 143
DegreeWorks Scribe | ANZ | 166 | 82 | 133
Project Manager | MENA | 127 | 63 | 102
Solution Architect | MENA | 148 | 76 | 119
Functional Consultant | MENA | 136 | 72 | 110
QA Engineer | MENA | 119 | 59 | 93
Integration Engineer | MENA | 110 | 55 | 85
Technical Architect | MENA | 144 | 72 | 114
Integration Lead | MENA | 153 | 80 | 123
Reporting Consultant | MENA | 140 | 68 | 106
Extensibility Engineer | MENA | 131 | 68 | 106
DegreeWorks Scribe | MENA | 123 | 61 | 98

## Assumptions & Inputs
Parameter | Value
Created | Initial workbook creation

## Sources
Source | Timestamp | Notes
N2S_Estimator_v1.xlsx (referenced) | 2024-01-01 | Base configuration data
fy25q3-ps-efficiency-model-02.xlsx (referenced) | 2024-01-01 | Role catalog reference